**2023 Annual Implementation Plan**

Submitted for review by Rachel Corben (School Principal) on 23 February, 2023 at 05:13 PM
Awaiting endorsement by Senior Education Improvement Leader

**for improving student outcomes**

Carlton North Primary School (1252)



**Self-evaluation Summary - 2023**

|  |  |  |
| --- | --- | --- |
|  | FISO 2.0 Dimensions | Self-evaluation Level |
| **Teaching and Learning** | Documented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs | Excelling |
| Use of common and subject-specific high impact teaching and learning strategies as part of a shared and responsive teaching and learning model implemented through positive and supportive student-staff relationships |

|  |  |  |
| --- | --- | --- |
| **Assessment** | Systematic use of data and evidence to drive the prioritisation, development, and implementation of actions in schools and classrooms. | Embedding |
| Systematic use of assessment strategies and measurement practices to obtain and provide feedback on student learning growth, attainment and wellbeing capabilities |

|  |  |  |
| --- | --- | --- |
| **Leadership** | The strategic direction and deployment of resources to create and reflect shared goals and values; high expectations; and a positive, safe and orderly learning environment | Embedding |
| Shared development of a culture of respect and collaboration with positive and supportive relationships between students and staff at the core |

|  |  |  |
| --- | --- | --- |
| **Engagement** | Strong relationships and active partnerships between schools and families/carers, communities, and organisations to strengthen students’ participation and engagement in school | Excelling |
| Activation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school |

|  |  |  |
| --- | --- | --- |
| **Support** | Responsive, tiered and contextualised approaches and strong relationships to support student learning, wellbeing and inclusion | Excelling |
| Effective use of resources and active partnerships with families/carers, specialist providers and community organisations to provide responsive support to students |

|  |  |
| --- | --- |
| **Enter your reflective comments** | The School Improvement Team assessed the school against the FISO Continua. The Team used the recent School Review assessment against the FISO Continua in conjunction with the 2022 NAPLAN results and data from the Student Attitudes to School Survey, Staff Opinion Survey and Parent, Carers and Guardian Opinion Survey. SIT also met with Data Coach, Sue North, who had analysed the school's data and discussed further areas for growth and focus in 2023. SIT determined that we will continue to improve the student learning data in 2023 with a strong focus on differentiation in Numeracy. The school also needs to focus on a few specific areas and continuous learning to sustain excellence and equity in performance and practice. Future work in the area of Assessment includes improving staff data literacy and tracking student learning growth over the years. |
| **Considerations for 2023** | Considerations for 2023 include:- continued support through the TLI - MiniLit and MacqLit.- continuing the Student Excellence Program- Education Support Staff supporting approximately eight students funded under PSD.- continued support for students from disadvantaged backgrounds.- Mental Health Fund- Equity Funding |
| **Documents that support this plan** |  |

**SSP Goals Targets and KIS**

|  |  |
| --- | --- |
| Goal 1 | In 2023 we will continue to focus on student learning - with an increased focus on numeracy - and student wellbeing through the 2023 Priorities Goal, a learning Key Improvement Strategy and a wellbeing Key Improvement Strategy. |
| Target 1.1 | Support for the 2023 Priorities |
| Key Improvement Strategy 1.aPriority 2023 Dimension  | Learning - Support both those who need scaffolding and those who have thrived to continue to extend their learning, especially in numeracy |
| Key Improvement Strategy 1.bPriority 2023 Dimension  | Wellbeing - Effectively mobilise available resources to support students' wellbeing and mental health, especially the most vulnerable |
| Goal 2 | To maximise learning growth in Literacy and Numeracy for all students. |
| Target 2.1 | By 2025 the percentage of students at or above benchmark growth in NAPLAN Reading to increase from 86% (2021) to 90%. |
| Target 2.2 | By 2025 the percentage of students at or above benchmark growth in NAPLAN Numeracy to increase from 64% (2021) to 90%. |
| Target 2.3 | By 2025 the percentage of students in the top two bands of NAPLAN Year 3 Writing will increase from 54% (2021) to 70%. |
| Target 2.4 | By 2025 the percentage of students in the top two bands of NAPLAN Year 5 Numeracy will increase from 40% (2021) to 50%. |
| Target 2.5 | By 2025 to increase the percentage of positive endorsement for the Academic emphasis factor on the Staff Opinion Survey from 69% (2021) to 80%.      |
| Target 2.6 | By 2025 increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey from 76% (2021) to 85%. |
| Key Improvement Strategy 2.aDocumented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs  | Utilise Professional Learning Communities to further develop teacher knowledge and instructional practice to differentiate student learning to their point of need. |
| Key Improvement Strategy 2.bDocumented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs  | To improve teacher data literacy and rigorous collaborative practices to plan, measure and evaluate the impact of teaching and learning. |
| Key Improvement Strategy 2.cDocumented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs  | To build teacher capacity to provide appropriate challenge and support for all students.  |
| Goal 3 | To empower students to have agency in their learning.  |
| Target 3.1 | By 2025 to increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey from 79% (2021) to 90%. |
| Target 3.2 | By 2025 to increase the percentage of positive endorsement for the Student Voice and Agency factor on the Student Attitudes to School Survey from 83% (2021) to 90%. |
| Target 3.3 | By 2025 to increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey from 77% (2021) to 90% |
| Key Improvement Strategy 3.aActivation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school  | To develop and implement a common language, understanding and practice of student learner agency. |
| Key Improvement Strategy 3.bDocumented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs  | To implement High Impact Teaching strategies that foster student agency. |
| Key Improvement Strategy 3.cActivation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school  | To provide opportunities for authentic student leadership. |
| Goal 4 | To enhance student wellbeing. |
| Target 4.1 | By 2025 to increase the percentage of positive endorsement for Teacher Concern factor in the Teacher Student Relations domain on the Student Attitudes to School Survey from 75% (2021) to 90%. |
| Target 4.2 | By 2025 to increase the percentage of students with Normal to High Resilience in the Individual Social and Emotional Wellbeing domain in the Student Attitudes to School Survey from 76% (2021) to 90%. |
| Key Improvement Strategy 4.aResponsive, tiered and contextualised approaches and strong relationships to support student learning, wellbeing and inclusion  | Consolidate the implementation of school-wide wellbeing programs.  |
| Key Improvement Strategy 4.bThe strategic direction and deployment of resources to create and reflect shared goals and values; high expectations; and a positive, safe and orderly learning environment  | Contribute to system leadership in wellbeing. |
| Key Improvement Strategy 4.cSystematic use of assessment strategies and measurement practices to obtain and provide feedback on student learning growth, attainment and wellbeing capabilities  | Investigate appropriate tools and data to evaluate and further improve wellbeing practices.  |

**Select Annual Goals and KIS**

|  |  |  |  |
| --- | --- | --- | --- |
| Four Year Strategic Goals | Is this selected for focus this year? | **Four Year Strategic Targets** | 12 month targetThe 12 month target is an incremental step towards meeting the 4-year target, using the same data set. |
| In 2023 we will continue to focus on student learning - with an increased focus on numeracy - and student wellbeing through the 2023 Priorities Goal, a learning Key Improvement Strategy and a wellbeing Key Improvement Strategy. | Yes | Support for the 2023 Priorities | Increase the percentage of students at or above benchmark growth in NAPLAN Reading to 87%.Increase the percentage of students at or above benchmark growth in NAPLAN Numeracy to 70%.Increase the percentage of students in the top two bands of NAPLAN Year 3 Writing to 57%.Increase the percentage of students in the top two bands of NAPLAN Year 5 Numeracy to 40%.Increase the percentage of positive endorsement for the Academic Emphasis factor on the Staff Opinion Survey to 75%. Increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey to 76%.  |
| To maximise learning growth in Literacy and Numeracy for all students. | No | By 2025 the percentage of students at or above benchmark growth in NAPLAN Reading to increase from 86% (2021) to 90%. |  |
| By 2025 the percentage of students at or above benchmark growth in NAPLAN Numeracy to increase from 64% (2021) to 90%. |  |
| By 2025 the percentage of students in the top two bands of NAPLAN Year 3 Writing will increase from 54% (2021) to 70%. |  |
| By 2025 the percentage of students in the top two bands of NAPLAN Year 5 Numeracy will increase from 40% (2021) to 50%. |  |
| By 2025 to increase the percentage of positive endorsement for the Academic emphasis factor on the School Staff Survey from 69% (2021) to 80%.      |  |
| By 2025 increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey from 76% (2021) to 85%. |  |
| To empower students to have agency in their learning.  | Yes | By 2025 to increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey from 79% (2021) to 90%. | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%. |
| By 2025 to increase the percentage of positive endorsement for the Student Voice and Agency factor on the Student Attitudes to School Survey from 83% (2021) to 90%. | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Student Attitudes to 90%. |
| By 2025 to increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey from 77% (2021) to 90% | Increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey to 85%. |
| To enhance student wellbeing. | Yes | By 2025 to increase the percentage of positive endorsement for Teacher Concern factor in the Teacher Student Relations domain on the Student Attitudes to School Survey from 75% (2021) to 90%. | Increase the percentage of positive endorsement for Teacher Concern factor in the Teacher Student Relations domain on the Student Attitudes to School Survey to 85%. |
| By 2025 to increase the percentage of students with Normal to High Resilience in the Individual Social and Emotional Wellbeing domain in the Student Attitudes to School Survey from 76% (2021) to 90%. | Increase the percentage of students with Normal to High Resilience in the Individual Social and Emotional Wellbeing domain in the Student Attitudes to School Survey to 80%. |

|  |  |
| --- | --- |
| Goal 1 | In 2023 we will continue to focus on student learning - with an increased focus on numeracy - and student wellbeing through the 2023 Priorities Goal, a learning Key Improvement Strategy and a wellbeing Key Improvement Strategy. |
| 12 Month Target 1.1 | Increase the percentage of students at or above benchmark growth in NAPLAN Reading to 87%.Increase the percentage of students at or above benchmark growth in NAPLAN Numeracy to 70%.Increase the percentage of students in the top two bands of NAPLAN Year 3 Writing to 57%.Increase the percentage of students in the top two bands of NAPLAN Year 5 Numeracy to 40%.Increase the percentage of positive endorsement for the Academic Emphasis factor on the Staff Opinion Survey to 75%. Increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey to 76%.  |
| **Key Improvement Strategies** | Is this KIS selected for focus this year? |
| **KIS 1**Priority 2023 Dimension | Learning - Support both those who need scaffolding and those who have thrived to continue to extend their learning, especially in numeracy | Yes |
| **KIS 2**Priority 2023 Dimension | Wellbeing - Effectively mobilise available resources to support students' wellbeing and mental health, especially the most vulnerable | Yes |
| Explain why the school has selected this KIS as a focus for this year. Please make reference to the self-evaluation, relevant school data, the progress against School Strategic Plan (SSP) goals, targets, and the diagnosis of issues requiring particular attention. | Please leave this field empty. Schools are not required to provide a rationale as this is in line with system priorities for 2023. |
| Goal 2 | To empower students to have agency in their learning.  |
| 12 Month Target 2.1 | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%. |
| 12 Month Target 2.2 | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Student Attitudes to 90%. |
| 12 Month Target 2.3 | Increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey to 85%. |
| **Key Improvement Strategies** | Is this KIS selected for focus this year? |
| **KIS 1**Activation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school | To develop and implement a common language, understanding and practice of student learner agency. | Yes |
| **KIS 2**Documented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs | To implement High Impact Teaching strategies that foster student agency. | Yes |
| **KIS 3**Activation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school | To provide opportunities for authentic student leadership. | Yes |
| Explain why the school has selected this KIS as a focus for this year. Please make reference to the self-evaluation, relevant school data, the progress against School Strategic Plan (SSP) goals, targets, and the diagnosis of issues requiring particular attention. | Carlton North Primary School underwent the School Review Process at the start of 2022. The School Strategic Plan for 2022-2026 has recently been finalised. Therefore, these Key Improvement Strategies are current and reflect the areas of improvement for Carlton North Primary school in 2023. |
| Goal 3 | To enhance student wellbeing. |
| 12 Month Target 3.1 | Increase the percentage of positive endorsement for Teacher Concern factor in the Teacher Student Relations domain on the Student Attitudes to School Survey to 85%. |
| 12 Month Target 3.2 | Increase the percentage of students with Normal to High Resilience in the Individual Social and Emotional Wellbeing domain in the Student Attitudes to School Survey to 80%. |
| **Key Improvement Strategies** | Is this KIS selected for focus this year? |
| **KIS 1**Responsive, tiered and contextualised approaches and strong relationships to support student learning, wellbeing and inclusion | Consolidate the implementation of school-wide wellbeing programs.  | Yes |
| **KIS 2**The strategic direction and deployment of resources to create and reflect shared goals and values; high expectations; and a positive, safe and orderly learning environment | Contribute to system leadership in wellbeing. | Yes |
| **KIS 3**Systematic use of assessment strategies and measurement practices to obtain and provide feedback on student learning growth, attainment and wellbeing capabilities | Investigate appropriate tools and data to evaluate and further improve wellbeing practices.  | No |
| Explain why the school has selected this KIS as a focus for this year. Please make reference to the self-evaluation, relevant school data, the progress against School Strategic Plan (SSP) goals, targets, and the diagnosis of issues requiring particular attention. | Carlton North Primary School underwent the School Review Process at the start of 2022. The School Strategic Plan for 2022-2026 has recently been finalised. Therefore, these Key Improvement Strategies are current and reflect the areas of improvement for Carlton North Primary school in 2023. |

**Define Actions, Outcomes and Activities**

|  |  |
| --- | --- |
| Goal 1 | **2023 Priorities Goal**In 2023 we will continue to focus on student learning - with an increased focus on numeracy - and student wellbeing through the 2023 Priorities Goal, a learning Key Improvement Strategy and a wellbeing Key Improvement Strategy. |
| 12 Month Target 1.1 | Increase the percentage of students at or above benchmark growth in NAPLAN Reading to 87%.Increase the percentage of students at or above benchmark growth in NAPLAN Numeracy to 70%.Increase the percentage of students in the top two bands of NAPLAN Year 3 Writing to 57%.Increase the percentage of students in the top two bands of NAPLAN Year 5 Numeracy to 40%.Increase the percentage of positive endorsement for the Academic Emphasis factor on the Staff Opinion Survey to 75%. Increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey to 76%.  |
| KIS 1Priority 2023 Dimension | Learning - Support both those who need scaffolding and those who have thrived to continue to extend their learning, especially in numeracy |
| **Actions** | To maximise learning growth in Literacy and Numeracy for all students.Utilise Professional Learning Communities to further develop teacher knowledge and instructional practice to differentiate student learning to their point of need.Build staff capacity in assessment and differentiation in Numeracy in order to identify and meet students’ individual learning needs, with a focus on the PLC cycle.Improve staff data literacy in the use of the SPA Platform to monitor student learning growth from year to year and across their primary school years at CNPS. |
| **Outcomes** | Professional Learning Teams utilise the Professional Learning Community (PLC) cycle to further differentiate to cater for individual student learning needs.Improved student learning outcomes as identified in 12 month targets. |
| **Success Indicators** | NAPLAN Data:Increase the percentage of students at or above benchmark growth in NAPLAN Reading to increase from 86% (2021) to 87%.Increase the percentage of students at or above benchmark growth in NAPLAN Numeracy to increase from 64% (2021) to 70%.Increase the percentage of students in the top two bands of NAPLAN Year 3 Writing will increase from 51% (2022) to 57%.Increase the percentage of students in the top two bands of NAPLAN Year 5 Numeracy will increase from 35% (2022) to 40%.Staff Opinion Survey Data:Increase the percentage of positive endorsement for the Academic Emphasis factor on the Staff Opinion Survey from 64% (2022) to 75%. Increase the percentage of positive endorsement of the Teacher Collaboration factor on the Staff Opinion Survey from 69% (2022) to 76%. |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| Continue to embed the CNPS Teaching and Learning Models. | 🗹 All Staff | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Implement the PLC cycle within PLTs to monitor student learning growth in Reading, Writing, Mathematics and Wellbeing. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Schedule first PLC inquiry cycle to begin at the start of Term 1 with a focus on Place Value. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🗹 PLP Priority | from:Term 1to:Term 1 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Schedule first PLC showcase in Term 2 and incorporate learnings into plans for school improvement. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 PLC Leaders🗹 Principal | 🗹 PLP Priority | from:Term 2to:Term 2 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Revise peer observation process with a focus on differentiation in Numeracy lessons. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $4,239.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Organise Learning Walks to observe staff practice and collect data on student experiences of Numeracy assessment and differentiation. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $4,239.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Leadership to attend SPA Professional Learning and conduct PL for staff. | 🗹 Assessment & Reporting Coordinator🗹 Assistant Principal🗹 Data Leader🗹 Learning Specialist(s)🗹 PLT Leaders🗹 Principal🗹 School Improvement Team | 🗹 PLP Priority | from:Term 1to:Term 2 | $3,855.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| PLCs use SPA to track student learning growth and inform PLC cycles. | 🗹 PLC Leaders🗹 Teacher(s) | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Engage Ryan Dunn to conduct Mathematics PL for staff on Day 1 Curriculum Day.  | 🗹 Learning Specialist(s)🗹 Teacher(s) | 🗹 PLP Priority | from:Term 1to:Term 1 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Engage Michael Minas to conduct PL for staff throughout the year to work with staff on differentiation in Numeracy. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal | 🗹 PLP Priority | from:Term 1to:Term 4 | $4,400.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Develop a professional learning plan that supports staff to identify and meet students’ individual Numeracy learning needs. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $3,690.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review the assessment schedule and embed time for moderation of Numeracy assessment in the professional learning calendar. | 🗹 Assessment & Reporting Coordinator🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Continue the implementation of MiniLit and MacqLit to provide intervention for Literacy across the school. | 🗹 Assistant Principal🗹 Education Support🗹 Literacy Support | 🞎 PLP Priority | from:Term 1to:Term 4 | $15,725.00🗹 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Continue the implementation of the Student Excellence Program to support high-ability students across the school. | 🗹 Assistant Principal | 🞎 PLP Priority | from:Term 1to:Term 4 | $6,725.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| KIS 2Priority 2023 Dimension | Wellbeing - Effectively mobilise available resources to support students' wellbeing and mental health, especially the most vulnerable |
| **Actions** | Consolidate the implementation of schoolwide wellbeing programs. Develop a succession plan for the School Therapy Dog Program.Address the perspective of bullying within the school and clearly articulate the school's stance and sequential response to any reported bullying. |
| **Outcomes** | Improved schoolwide practice of wellbeing programs.Improved and clearly communicated processes for managing bullying.Improved student connectedness to school. |
| **Success Indicators** | Attitude to School Survey Data:Increase the percentage of positive endorsement for Advocate at School to 92%.Increase the percentage of positive endorsement for Managing Bullying to 88%.Increase the percentage of positive endorsement for Respect for Diversity to 90%.Increase the percentage of positive endorsement for Teacher Concern to 82%.Increase the percentage of positive endorsement for Attitudes to Attendance to 93%.Increase the percentage of positive endorsement for Sense of Connectedness to 88%. |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| Develop succession and sustainability plan for School Therapy Dogs program. | 🗹 Principal | 🞎 PLP Priority | from:Term 1to:Term 1 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Identify Staff and their dogs to undergo Lead the Way Animal Assisted Therapy Course/Training. | 🗹 Principal | 🗹 PLP Priority | from:Term 1to:Term 1 | $8,066.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🗹 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Develop a Therapy Dogs Attendance Schedule. | 🗹 Principal | 🞎 PLP Priority | from:Term 1to:Term 3 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Provide Professional Learning for all Staff on the positive impact of Therapy Dogs in Schools | 🗹 Principal | 🗹 PLP Priority | from:Term 3to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🗹 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Employ an ES to implement Animal Assisted Therapy with School Therapy Dog when required. | 🗹 Principal | 🞎 PLP Priority | from:Term 1to:Term 4 | $21,310.90🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🗹 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Implement Respectful Relationships Curriculum to address perceptions of bullying at the school. | 🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Document the processes for addressing incidents of bullying and communicate schoolwide. | 🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Participate in the MoRE Pilot Program - Modelling Respect and Equality. | 🗹 All Staff🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Engage DET Staff from Region to conduct professional learning for all staff in personal wellbeing and self care. | 🗹 All Staff | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Adapt and integrate Expect Respect materials to reduce bullying behaviour consistent with SWPBS logic. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Staff to undertake professional learning through the Butterfly Foundation. Self-nominated staff to complete the Body Bright Training and deliver lessons from the Body Bright Curriculum. | 🗹 Teacher(s) | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Adapt and integrate Expect Respect materials to reduce bullying behaviour consistent with SWPBS logic. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Engage Evolve - Bec Martin and Steve Villani to conduct 2 CyberSafety sessions during the school year to educate students in Years 3 to 6 on online safety at home and at school. Engage Evolve - Bec Martin and Steve Villani to conduct 1 Parent Information Session in Term 2 | 🗹 Assistant Principal🗹 Teacher(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $5,375.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Goal 2 | To empower students to have agency in their learning.  |
| 12 Month Target 2.1 | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%. |
| 12 Month Target 2.2 | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Student Attitudes to 90%. |
| 12 Month Target 2.3 | Increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey to 85%. |
| KIS 1Activation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school | To develop and implement a common language, understanding and practice of student learner agency. |
| **Actions** | Review existing processes to capture school and community views and understandings of student voice, agency and leadership. |
| **Outcomes** | Develop staff, students and parent/carers understanding of student voice, agency and leadership.  |
| **Success Indicators** | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%.Increase the percentage of positive endorsement for the Student Voice and Agency factor on the Student Attitudes to School Survey to 83%.Increase the percentage of positive endorsement for the Use Student Feedback to Improve Practice factor in the Teaching and Learning Evaluation module on the Staff Opinion Survey to 85%.  |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| Identify trends and correlations between different data sets to identify persisting or emerging issues in student engagement and the use of student voice, agency and leadership. This analysis could include: - using data from the Attitudes to School Survey and the Staff Opinion Survey to understand current levels of engagement and confidence - drawing on the FISO Dimension, Empowering Students and Building School Pride, to develop a school self-evaluation and identify potential areas for improvement.  | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| KIS 2Documented teaching and learning program based on the Victorian Curriculum and senior secondary pathways, incorporating extra-curricula programs | To implement High Impact Teaching strategies that foster student agency. |
| **Actions** | To continue to develop agreed processes and practice in developing student learning goals in Reading, Writing and Mathematics.  |
| **Outcomes** | Students are able to articulate their Learning Goals for Reading, Writing and Mathematics.Student Learning Goals shared on Seesaw to parents.Students/Teachers conferencing regularly to review and develop Learning Goals in Reading, Writing and Mathematics. |
| **Success Indicators** | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%.Increase the percentage of positive endorsement for the Student Voice and Agency factor on the Student Attitudes to School Survey to 83%. |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| Teachers will actively seek student feedback about their teaching practice using PIVOT Surveys. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team🗹 Teacher(s) | 🗹 PLP Priority | from:Term 1to:Term 4 | $2,244.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| School Improvement Team will review current practices across the school in conferencing and the development of Learning Goals. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Teachers will work in collaboration with students to identify Learning Goals in Reading, Writing and Mathematics. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team🗹 Teacher(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Continue to implement the FISO improvement cycle to embed conferencing with students to identify Learning Goals in collaboration to improve student agency in learning. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team🗹 Teacher(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| KIS 3Activation of student voice and agency, including in leadership and learning, to strengthen students’ participation and engagement in school | To provide opportunities for authentic student leadership. |
| **Actions** | To provide opportunities for students to engage and contribute to schoolwide improvement teams. |
| **Outcomes** | School Improvement Leaders and Student Representative Council to continue to contribute to School improvement.Opportunities provided for student membership in the following working parties:o RAPo Buildings and Grounds Subcommitteeo SWPB/RR Teamo Friends and Sporto Friends of The Artso Inclusion Working Partyo Building Refurbishment Grant Working Partyo Relevant Fundraising EventsStudents provided with opportunities to contribute to school policy development and review. |
| **Success Indicators** | Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Parent Opinion Survey to 85%.Increase the percentage of positive endorsement for the Student Agency and Voice factor on the Student Attitudes to School Survey to 88%.Increase the percentage of positive endorsement for the Student Voice and Agency factor on the Student Attitudes to School Survey to 83%.Students attend and actively participate in the following working parties:o RAPo Buildings and Grounds Subcommitteeo SWPB/RR Teamo Friends and Sporto Friends of The Artso Inclusion Working Partyo Building Refurbishment Grant Working Partyo Relevant Fundraising Events |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| Continue the School Improvement Leaders and Student Representative Council. | 🗹 Assistant Principal🗹 Principal🗹 School Leadership Team🗹 Teacher(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Provide opportunities for membership in the following working parties:- RAP- Buildings and Grounds Subcommittee- SWPB/RR Team- Friends and Sport- Friends of The Arts- Inclusion Working Party- Building Refurbishment Grant Working Party- Relevant Fundraising Events | 🗹 Assistant Principal🗹 Principal🗹 Student(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Provide opportunities for students to contribute to school policy development and review. | 🗹 Assistant Principal🗹 Principal🗹 Student(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Co-designing opportunities for students to initiate school events, and to engage in planning and facilitating them.  | 🗹 Assistant Principal🗹 Principal🗹 Student(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Goal 3 | To enhance student wellbeing. |
| 12 Month Target 3.1 | Increase the percentage of positive endorsement for Teacher Concern factor in the Teacher Student Relations domain on the Student Attitudes to School Survey to 85%. |
| 12 Month Target 3.2 | Increase the percentage of students with Normal to High Resilience in the Individual Social and Emotional Wellbeing domain in the Student Attitudes to School Survey to 80%. |
| KIS 1Responsive, tiered and contextualised approaches and strong relationships to support student learning, wellbeing and inclusion | Consolidate the implementation of school-wide wellbeing programs.  |
| **Actions** | Strengthen implementation of the whole school approach to Respectful Relationships and Schoolwide Positive Behaviour Supports through data analysis, feedback and surveys.Implement Schoolwide Positive Behaviours Supports (SWPBS), Universal Positive Behaviours (UPB) and Classroom Strategies (CS) with fidelity. |
| **Outcomes** | Respectful Relationships:Students understand and practice respectful relationships.Students know where to seek help and are able to use their help-seeking skills when required.Students use a range of positive coping strategies.Teachers’ interactions with students, colleagues and others demonstrate respectful, gender-equitable and inclusive behaviours and language.Teachers and students challenge disrespectful attitudes and behaviours, inequality and limiting and harmful gender stereotypes.Teachers explicitly teach and assess social and emotional learning, respectful relationships and consent education Respectful RR/SWPBS Team driving and promoting the initiative across the school community.All staff understand the importance of promoting gender equality and respectful relationships in the prevention of family and gender-based violence. Students and school staff show an increase in positive behaviours and attitudes towards gender equality.Respectful Relationships is embedded in curriculum documentation across all year levels.Leaders actively promote, advocate for and support a whole school approach to Respectful Relationships. Leaders model respectful behaviours and gender-equitable treatment of students, staff and the broader school community.Schoolwide Positive Behaviour Support:Improved attendance/lateness.Improved teacher-student relationships (AttoSS). Increase the percentage of positive endorsement for Teacher Concern to 85%.Staff use a higher rate and wider range of opportunities to respond.Increased willingness of staff to provide peer observation, access feedback, and access coaching. Review the strength of Tier 1 instructional program and develop responses to develop it further.Support all staff to look for areas of improvement in Tier 1 instructional program. |
| **Success Indicators** | Respectful Relationships:Documented Respectful Relationships Action Plan.100% of staff have engaged in professional learning about Respectful Relationships.Curriculum documentation and timetable shows plans for explicit teaching of the Respectful Relationships curriculum across all year levels, including consent education.School policies model Respectful Relationships and gender equality practices across the school.Staff and students understand where they can seek help and support on any issue related to family violence, and age-appropriate information about specialist family violence and sexual assault services is visible on posters around the school.Data sources indicate a sustained improvement in positive attitudes, behaviours and gender equality across the school community. For example, Student Attitudes Towards School Survey (School Safety, Social Engagement, Teacher-Student relations and Not Experiencing Bullying factors); Attendance data.Schoolwide Positive Behaviour Support:Increase the percentage of positive endorsement of Classroom Behaviour to 92%.Archives of systems to support practices (artefacts)SWPBS Annual Evaluation Report (looking at fidelity assessment and evaluating the impact on student outcomes)Improve behaviour data. Triangle Tool visual available for Term 3 and Term 4. Staff professional voice and ongoing commitment to SWPBS implementation by building trust, respect, and shared responsibility.SWPBS Team supports the school leadership team to integrate analysis of academic and behaviour data.SWPBS Team uses data with confidence to evaluate the effectiveness of the Action plan and of implementation outcomes (Triangle Tool, Big 5). Develop, monitor and report on the implementation of the 2023 CNPS SWPBS Action Plan.Systems developed to ensure practices can be implemented and monitored as outlined in the SWPBS Action Plan.Monitoring practices' implementation and move towards adult consistency and collective efficacy across the school. Work with School Leadership to create a visual representation of tiers (putting faces on the data) for academics and behaviour.We will use the following data/evidence to measure the success of the Outcomes relating to implementing the SWPBS framework.Archives of systems to support practices (artefacts)2023 UPP Action Plan + 80% completedExternally facilitated TFI SWPBS Annual Evaluation Report (looking at fidelity assessment and evaluating the impact on student outcomes)Increase student engagement area of 'Effective Classroom Behaviour' to 90%.Triangle Tool graph available for Academics and Behaviour - each showing growth in the proportion of students successful with Tier 1 instructional and behavioural programs. Improve behaviour data. Increase the amount of instructional time all students can access.  |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| RR/SWPBS Team to include parent and student membership, and embed opportunity for student voice in team processes. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $1,560.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🗹 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Conduct a school baseline assessment to explore how gender equality and respectful relationships are currently promoted. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 2 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| RR/SWPBS Team to review the Respectful Relationships Action Plan that maps the school’s priorities over the 6 elements of the whole school approach.  | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Update school meeting schedule to ensure the RR/SWPBS Team has time to meet, plan/work together and work with SWPBS and RR Coaches regularly. | 🗹 Assistant Principal🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review staff professional learning needs in Respectful Relationships and Schoolwide Positive Behaviour Support and develop strategies to address any gaps. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Include time for Respectful Relationships Education planning as a standing item on curriculum planning meeting agendas. | 🗹 All Staff🗹 Assistant Principal🗹 PLT Leaders🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Schedule and plan engagement in key national events including the 16 Days of Activism Against Gender Based Violence. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Continue to develop the systems and practices to implement the 7 SWPBS Tier 1 Essential Features with fidelity. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Build staff capacity to implement core SWPBS practices consistently across the school and understand basic behaviour principles including the foundations of SWPBS (Applied Behaviour Analysis). Team to lead PL sessions using Vic SWPBS resources, find a way to reach all staff including ES. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review the Schoolwide Matrix and setting-specific signage to support staff in non-classroom settings, the whole-school acknowledgement system and a behaviour-response flowchart. | 🗹 All Staff🗹 Assistant Principal🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Enhance existing tiered supports for children who are identified as requiring additional academic, behavioural, and wellbeing assistance to reduce the frequency of problem behaviours that impact on social and learning outcomes. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| SWPBS Implementation Team will use the SUBSIST Checklist to identify top 3 priorities for SWPBS implementation sustainability.  | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Complete UPB action plan and meet readiness indicators for Classroom Systems by Term 4 Week 4. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 3 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Complete Vic SWPBS Classroom Systems training and RR/SWPBS Team to trial the different classroom practices and provide action research feedback to staff. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Identify tools for collecting data to assess and monitor progress and create mechanisms for ongoing feedback on experiences of gender equality across the school community. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Support the RR/SWPBS to facilitate termly student focus groups to gain feedback about the effectiveness of implementation and to guide future planning and actions.  | 🗹 Assistant Principal🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review the way information is gathered to ensure data is captured regarding student use of coping strategies and help-seeking skills. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review data collected regarding student incidents to ensure it is able to enable disaggregation by gender, year level and location, and also by the type of inter-personal violence (if any). | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Review and update documented behaviour expectations and consequences to ensure actions to address drivers of violence are included. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| Refine data collection and analysis systems to support problem-solving and long-term SWPBS implementation. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |
| KIS 2The strategic direction and deployment of resources to create and reflect shared goals and values; high expectations; and a positive, safe and orderly learning environment | Contribute to system leadership in wellbeing. |
| **Actions** | Work in collaboration with Cluster Schools and support other schools within NEMA implementing RR across NEMA. |
| **Outcomes** | Supported cluster schools with the implementation of Respectful Relationships (RR) within their schools.Connect with cluster schools to engage with cross-school support in Respectful Relationships (RR). |
| **Success Indicators** | Carlton North Primary School identified as a Lead School for respectful Relationships. Evidence of collaboration with cluster schools.Evidence of regularly scheduled meetings with cluster schools. |
| Activities and Milestones | People Responsible | Is this a PL Priority | When | Funding Streams |
| To work within a community of Practice with Cluster Schools and support other schools within NEMA implementing RR across NEMA. | 🗹 Assistant Principal🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $5,652.00🞎 Equity funding will be used🞎 Disability Inclusion Tier 2 Funding will be used🞎 Schools Mental Health Menu items will be used which may include DET funded or free items |

**Funding Planner**

Summary of Budget and Allocated Funding

|  |  |  |  |
| --- | --- | --- | --- |
| **Summary of Budget** | **School’s total funding ($)** | **Funding Allocated in activities ($)** | **Still available/shortfall** |
| Equity Funding | $0.00 | $15,725.00 | -$15,725.00 |
| Disability Inclusion Tier 2 Funding | $0.00 | $0.00 | $0.00 |
| Schools Mental Health Fund and Menu | $0.00 | $31,436.90 | -$31,436.90 |
| **Total** | $0.00 | $47,161.90 | -$47,161.90 |

Activities and Milestones – Total Budget

|  |  |
| --- | --- |
| **Activities and Milestones** | **Budget** |
| Continue the implementation of MiniLit and MacqLit to provide intervention for Literacy across the school. | $15,725.00 |
| Identify Staff and their dogs to undergo Lead the Way Animal Assisted Therapy Course/Training. | $8,066.00 |
| Provide Professional Learning for all Staff on the positive impact of Therapy Dogs in Schools | $0.00 |
| Employ an ES to implement Animal Assisted Therapy with School Therapy Dog when required. | $21,310.90 |
| RR/SWPBS Team to include parent and student membership, and embed opportunity for student voice in team processes. | $1,560.00 |
| **Totals** | $46,661.90 |

Activities and Milestones - Equity Funding

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| Continue the implementation of MiniLit and MacqLit to provide intervention for Literacy across the school. | from:Term 1to:Term 4 | $15,725.00 | 🗹 School-based staffing |
| **Totals** |  | $15,725.00 |  |

Activities and Milestones - Disability Inclusion Funding

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| **Totals** |  | $0.00 |  |

Activities and Milestones - Schools Mental Health Fund and Menu

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| Identify Staff and their dogs to undergo Lead the Way Animal Assisted Therapy Course/Training. | from:Term 1to:Term 1 | $8,066.00 | 🗹 Lead the Way Therapy Dogs **This activity will use Mental Health Menu staffing*** + Build staff capacity (conference, course, seminar)
 |
| Provide Professional Learning for all Staff on the positive impact of Therapy Dogs in Schools | from:Term 3to:Term 4 | $500.00 | 🗹 Lead the Way Therapy Dogs **This activity will use Mental Health Menu staffing*** + Build staff capacity (conference, course, seminar)
 |
| Employ an ES to implement Animal Assisted Therapy with School Therapy Dog when required. | from:Term 1to:Term 4 | $21,310.90 | 🗹 Employ staff to support Tier 1 activities **This activity will use Mental Health Menu staffing*** + Assign existing staff member to initiative (eduPay)
 |
| RR/SWPBS Team to include parent and student membership, and embed opportunity for student voice in team processes. | from:Term 1to:Term 4 | $1,560.00 | 🗹 Respectful Relationships (free) **This activity will use Mental Health Menu staffing*** + Employ CRT to release staff member
 |
| **Totals** |  | $31,436.90 |  |

Additional Funding Planner – Total Budget

|  |  |
| --- | --- |
| **Activities and Milestones** | **Budget** |
| **Totals** | $0.00 |

Additional Funding Planner – Equity Funding

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| **Totals** |  | $0.00 |  |

Additional Funding Planner – Disability Inclusion Funding

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| **Totals** |  | $0.00 |  |

Additional Funding Planner – Schools Mental Health Fund and Menu

|  |  |  |  |
| --- | --- | --- | --- |
| **Activities and Milestones** | **When** | **Funding allocated ($)** | **Category** |
| **Totals** |  | $0.00 |  |

**Professional Learning and Development Plan**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Learning Priority | Who | When | Key Professional Learning Strategies | Organisational Structure | Expertise Accessed | Where |
| Implement the PLC cycle within PLTs to monitor student learning growth in Reading, Writing, Mathematics and Wellbeing. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | from:Term 1to:Term 4 | 🗹 Formalised PLC/PLTs | 🗹 PLC/PLT Meeting | 🗹 PLC Initiative | 🗹 On-site |
| Schedule first PLC inquiry cycle to begin at the start of Term 1 with a focus on Place Value. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team | from:Term 1to:Term 1 | 🗹 Planning🗹 Formalised PLC/PLTs | 🗹 PLC/PLT Meeting | 🗹 PLC Initiative | 🗹 On-site |
| Schedule first PLC showcase in Term 2 and incorporate learnings into plans for school improvement. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 PLC Leaders🗹 Principal | from:Term 2to:Term 2 | 🗹 Planning🗹 Formalised PLC/PLTs | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 PLC Initiative | 🗹 On-site |
| Leadership to attend SPA Professional Learning and conduct PL for staff. | 🗹 Assessment & Reporting Coordinator🗹 Assistant Principal🗹 Data Leader🗹 Learning Specialist(s)🗹 PLT Leaders🗹 Principal🗹 School Improvement Team | from:Term 1to:Term 2 | 🗹 Planning | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 External consultantsSPA | 🗹 On-site |
| PLCs use SPA to track student learning growth and inform PLC cycles. | 🗹 PLC Leaders🗹 Teacher(s) | from:Term 1to:Term 4 | 🗹 Formalised PLC/PLTs | 🗹 PLC/PLT Meeting | 🗹 PLC Initiative | 🗹 On-site |
| Engage Ryan Dunn to conduct Mathematics PL for staff on Day 1 Curriculum Day.  | 🗹 Learning Specialist(s)🗹 Teacher(s) | from:Term 1to:Term 1 | 🗹 Planning🗹 Preparation🗹 Curriculum development | 🗹 Whole School Pupil Free Day | 🗹 External consultantsRyan Dunn | 🗹 On-site |
| Engage Michael Minas to conduct PL for staff throughout the year to work with staff on differentiation in Numeracy. | 🗹 All Staff🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation🗹 Curriculum development | 🗹 Whole School Pupil Free Day | 🗹 External consultantsMichael Minas | 🗹 On-site |
| Identify Staff and their dogs to undergo Lead the Way Animal Assisted Therapy Course/Training. | 🗹 Principal | from:Term 1to:Term 1 | 🗹 Planning🗹 Preparation | 🗹 Professional Practice Day | 🗹 External consultantsLead the Way Institute | 🗹 Off-siteLead the Way Institute |
| Provide Professional Learning for all Staff on the positive impact of Therapy Dogs in Schools | 🗹 Principal | from:Term 3to:Term 4 | 🗹 Planning🗹 Preparation🗹 Demonstration lessons | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 External consultantsLead the Way Institute | 🗹 On-site |
| Participate in the MoRE Pilot Program - Modelling Respect and Equality. | 🗹 All Staff🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation🗹 Collaborative Inquiry/Action Research team | 🗹 Network Professional Learning | 🗹 Departmental resourcesRespectful Relationships | 🗹 On-site |
| Engage DET Staff from Region to conduct professional learning for all staff in personal wellbeing and self care. | 🗹 All Staff | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation🗹 Individualised Reflection | 🗹 Whole School Pupil Free Day | 🗹 Departmental resourcesCareer Starter Pilot Staff | 🗹 On-site |
| Staff to undertake professional learning through the Butterfly Foundation. Self-nominated staff to complete the Body Bright Training and deliver lessons from the Body Bright Curriculum. | 🗹 Teacher(s) | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation | 🗹 Timetabled Planning Day | 🗹 Maths/Sci Specialist🗹 External consultantsButterfly Bright Foundation | 🗹 On-site |
| Adapt and integrate Expect Respect materials to reduce bullying behaviour consistent with SWPBS logic. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 Departmental resourcesSWPBS | 🗹 On-site |
| Teachers will actively seek student feedback about their teaching practice using PIVOT Surveys. | 🗹 Assistant Principal🗹 Learning Specialist(s)🗹 Principal🗹 School Improvement Team🗹 Teacher(s) | from:Term 1to:Term 4 | 🗹 Individualised Reflection | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 External consultantsPIVOT Survey | 🗹 On-site |
| Build staff capacity to implement core SWPBS practices consistently across the school and understand basic behaviour principles including the foundations of SWPBS (Applied Behaviour Analysis). Team to lead PL sessions using Vic SWPBS resources, find a way to reach all staff including ES. | 🗹 Principal🗹 Respectful Relationships Implementation Team🗹 SWPBS Leader/Team | from:Term 1to:Term 4 | 🗹 Planning🗹 Preparation🗹 Collaborative Inquiry/Action Research team | 🗹 Formal School Meeting / Internal Professional Learning Sessions | 🗹 Departmental resourcesSWPBS Coach | 🗹 On-site |